## Sheet1
Milestones |  | Remarks | Q2 2020 | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022
Phase 1: Business | Product requirements defined
Intial investor funding secured
prototype production cost
test cost
operational cost (if any)
FMEA defined
| 0th MVP produced | initial technology solution demonstrated (object classification)
Phase 2: R&D | Engineering specifications defined
hardware engineering specs defined
software engineering specs defined
Test methods defined
Get test equipment (for hardware eng)
Setup tests
| BUILD AND TEST | iterative, to have regular updates
| 1st MVP produced | all high risk FMEAs closed, all SHALL+MUST requirements met
Phase 3: Scaling | Bill of Materials released
part requirements and QC defined
part and assembly drawings released
part supplier defined
| contract manufacturer (CM) defined | at the end of quarter.
Assembly plan aligned
sign-off assembly procedures and layout
assembly work instructions aligned with CM
QC plan aligned
buy-off end-of-line test equipment
trial run
| 1st full product released | all FMEA risks closed, all SHOULD requirements met
Phase 4: Manufacturing | Production
Yield improvement plan aligned
Design improvement plan aligned
End-of-life/ End-of-Production plan aligned
Future | Implement yield improvement plan | TBD
| Implement design improvement plan | TBD
| Implement EoL/EoP plan | TBD